## Sheet1
#VALUE! |  |  | Meeting Agenda/Notes
Bartow County Elections Renovation & Addition
3380 Blue Springs Road
Kennesaw, GA 30144
Purpose: | Bid Q&A |  | Project Number: | 2025-3042
Location: | Digitally (email) |  | Project Name: | Bartow County Elections Renovation & Addition
Chairperson: | Erica Guevara |  | Date/Time: | Q 6/19 - R 6/26; July 1st noon Bids (CMAR Bids) 3million estimated budget
# | Date | Question | Response
1 | 2026-06-17 | Will we be utilizing all of the existing asphalt and just restriping or are we required to install new asphalt and restripe at all parking spaces on pg. AS101? | Current scope includes restriping and new parking spaces will require new asphalt, patch/repair existing asphalt as needed. Reseal with blacktop, not a full asphalt coating.
2 | 2026-06-17 | Are there any additional specifications for the exterior cargo lift? | Specifications are currently in production. A specification and product will be selected in conjunction with the selected GC in the construction document phase.
3 | 2026-06-17 | Who is the current fire alarm manufacturer? | Honeywell whole building however warehouse has its own dedicated alarm (Resideo ap).
4 | 2026-06-17 | Will we be adding a sprinkler system to this building? | No.
5 | 2026-06-19 | Question for the paint. In the stairwells, are the railings, kickplates, risers and under portion of stairs to be painted along with gypsum board walls? | Stair scope includes paint on walls and base; new flooring at bottom will match adjacent hallway and top landing will be existing to remain.
6 |  | Requested Site Visit | Not at this time; GC will have a site visit once selected.