The following deliverables are scheduled for the project initiation phase.

| ID # | Deliverable Name | Due Date/ Frequency |  |
| --- | --- | --- | --- |
|  | Kickoff meeting | 15 Calendar Days after Contractor Engagement Start (CES) | To be scheduled. |
|  | Project Work Plan – Final | 45 Calendar Days after CES | To be created and maintained by new contractor |
|  | Contract Schedule – Final | 45 Calendar Days after CES | To be created and maintained by new contractor |
|  | Risk Management Plan | 45 Calendar Days after CES | To be created by new contractor |
|  | Risk Register | 45 Calendar Days after CES | To be created and maintained by new contractor |
|  | Project Issue Log | 45 Calendar Days after CES | To be created and maintained by new contractor |

The following deliverables are scheduled for the project execution phase, including Design, Development and Integration Testing.

| ID # | Deliverable Name | Due Date/ Frequency |  |
| --- | --- | --- | --- |
|  | Business Requirement Document (BRD) | Mutually agreed by the SCM and the Contractor, and approved by the SCM. | To be created by new contractor |
|  | Requirements Traceability Matrix (RTM) | Mutually agreed by the SCM and the Contractor, and approved by the SCM. | To be created and maintained by new contractor |
|  | Detailed Functional Design Document (DFDD) | Mutually agreed by the SCM and the Contractor, and approved by the SCM. | To be created by new contractor |
|  | Detailed Design Document (DDD) | Mutually agreed by the SCM and the Contractor, and approved by the SCM. | To be created by new contractor |
|  | Interface Control Document (ICD) | Mutually agreed by the SCM and the Contractor, and approved by the SCM. | To be created and maintained by new contractor |
|  | System Test Plan | Mutually agreed by the SCM and the Contractor, and approved by the SCM. | To be created by new contractor |
|  | System Test Case and Test Data | Mutually agreed by the SCM and the Contractor, and approved by the SCM. | To be created by new contractor |
|  | System Test Summary | Upon system test completion | To be created by new contractor |
|  | Monthly Project Status Report | Monthly | To be created by new contractor |
|  | Project Weekly Meeting | Weekly | To be created by new contractor |
|  | Project Weekly Status Report | Weekly | To be created by new contractor |
|  | Project Monthly Status Summary | Monthly | To be created by new contractor |

The following deliverables are scheduled for the cloud migration phase.

| ID # | Deliverable Name | Due Date/ Frequency |  |
| --- | --- | --- | --- |
|  | Cloud Infrastructure Plan – Final | 90 Calendar Days after CES | To be created by new contractor if not available at the time of contract award |
|  | Cloud Security Plan - Final | 90 Calendar Days after CES | To be created by new contractor if not available at the time of contract award |
|  | Cloud Network Plan – Final | 90 Calendar Days after CES | To be created by new contractor if not available at the time of contract award |
|  | Cloud Capacity Plan – Final | 90 Calendar Days after CES | To be created by new contractor if not available at the time of contract award |
|  | Cloud System Cutoff Plan – Final | 90 Calendar Days after CES | To be created by new contractor if not available at the time of contract award |
|  | Cloud Risk Management Plan – Final | 90 Calendar Days after CES | To be created by new contractor if not available at the time of contract award |
|  | Cloud Disaster Recovery Plan – Final | 90 Calendar Days after CES | To be created by new contractor if not available at the time of contract award |
|  | Data Migration Plan | 90 Calendar Days after CES | To be created by new contractor |
|  | System Logical Architecture Diagram | 90 Calendar Days after CES | To be transferred from incumbent contractor to new contractor and maintained by new contractor |
|  | System Physical Architecture Diagram | 90 Calendar Days after CES | To be transferred from incumbent contractor to new contractor and maintained by new contractor |
|  | Cloud Migration Weekly Status Report | Weekly | To be created by new contractor |
|  | Cloud Migration Monthly Status Summary | Monthly | To be created by new contractor |
|  | Cloud Migration Weekly Meeting | Weekly | To be created by new contractor |
|  | Cloud Platform Operations Manual/Helpdesk Guide | 210 Calendar Days after CES | To be created by new contractor if not available at the time of contract award |
|  | Cloud Migration Validation Result | At least three (3) weeks before the end of the cloud migration phase. | To be created by new contractor |
|  | Cloud Migration Completion Certificate | At least two (2) weeks before the end of the cloud migration phase. | To be created by new contractor |

The following deliverables are scheduled for the UAT phase.

| ID # | Deliverable Name | Due Date/ Frequency |  |
| --- | --- | --- | --- |
|  | Report Manual | 20 Calendar Days before the start of UAT. | To be transferred from incumbent contractor to new contractor and maintained by new contractor |
|  | User Manual | 20 Calendar Days before the start of UAT. | To be transferred from incumbent contractor to new contractor and maintained by new contractor |
|  | Training Plan | 30 Calendar Days before the start of UAT. | To be created by new contractor |
|  | UAT Readiness Certificate | At least 3 Calendar Days before the start of UAT release. | To be created by new contractor |
|  | Production Readiness Certificate | At least one (1) week before the start of production release. | To be created by new contractor |
|  | Release Notes (for UAT, and Production only) | One (1) week before the deployment of changes to UAT or production. | To be created by new contractor |
|  | Production Implementation Plan | 20 Calendar Days before the deployment of changes to production. | To be created by new contractor |
|  | Project Monthly Status Report | Monthly | To be created by new contractor |
|  | Project Weekly Meeting | Weekly | To be created by new contractor |
|  | Project Weekly Status Report | Weekly | To be created by new contractor |
|  | UAT Issue Log | Daily | To be created by new contractor |

The following deliverables are scheduled for the transition phase.

| ID # | Deliverable Name | Due Date/ Frequency |  |
| --- | --- | --- | --- |
|  | Transition Plan (Incoming) - Final | 45 Calendar Days after CES | To be created by new contractor |
|  | Staffing Plan – Final | 45 Calendar Days after CES | To be created by new contractor |
|  | Business Continuity Plan – Final | 45 Calendar Days after CES | To be transferred from incumbent contractor to new contractor and maintained by new contractor |
|  | Operations Manual/ Helpdesk Guide | At least 90 Calendar Days before the end of the transition phase. | To be transferred from incumbent contractor to new contractor and maintained by new contractor |
|  | System Handoff Certificate | At least 20 Calendar Days before the end of the transition phase. | To be created by new contractor |
|  | Monthly System Operations Status Report | Monthly | To be created by new contractor |

The following deliverables are scheduled for the system operations and maintenance phase.

| ID # | Deliverable Name | Due Date/ Frequency |  |
| --- | --- | --- | --- |
|  | Monthly System Operations Status Report | Monthly | To be created by new contractor |
|  | Monthly Maintenance Plan | Monthly | To be created by new contractor |
|  | End-of-Day (EOD) Processes Report | Daily | To be created by new contractor |
|  | Quarterly Resource Utilization Report | Quarterly | To be created by new contractor |
|  | Weekly Operations Meeting | Weekly | To be created by new contractor |
|  | System Issue Tracker | Ongoing | To be created and maintained by new contractor |
|  | Transition Plan (Outgoing) – Draft | 300 Calendar Days before the Contract ends | To be created by new contractor |
|  | Transition Plan (Outgoing) – Final | 240 Calendar Days before the Contract ends. | To be created by new contractor |