## SSP North
State Farm Sign (74) Locations 04/15/16
RT. 80 - 18 |  |  |  | RT. 280 - 10 |  |  |  | RT. 287 - 24
WB |  | EB |  | EB |  | WB |  | NB |  | SB
68 | NO | 35.8 | OK | 0.9 | 12.6 | 17 | 5.2 | 1.3 | OK | 44.6 | OK
67.7 | OK | 40.2 | OK | 4.2 | 16.8 | 15.5 | 0.8 | 6.2 | OK | 41.1 | OK
63.6 | OK | 44.7 | NO | 8.5 |  | 10.3 |  | 11.1 | OK | 37.6 | OK
61.4 | OK | 49.1 | NO | RT. 440 - 5 |  |  |  | 14.7 | OK | 34.3 | OK
57.8 | OK | 54.1 | OK | NB |  | SB |  | 19.4 | OK | 29.5 | OK
53 | NO | 59.1 | OK | 0.7 | OK | 3.8 | OK | 21.7 | NO | 25.9 | OK
47.9 | NO | 64.2 | OK | 2.8 | OK | 0.9 | OK | 26.9 | OK | 20.4 | OK
43.2 | NO | 68.1 | OK | 3.9 | OK |  |  | 30.4 | OK | 14.3 | OK
38.4 | OK | [6 empty] | 35 | OK | 9.5 | OK
35.3 | OK |  |  | RT. 78 - 19 |  |  |  | 38.5 | OK | 5.5 | OK
|  |  |  | WB |  | EB |  | 42.9 | OK | 0.5 | NO
|  |  |  | 58.1 L | OK | 27.6 | OK | 45 | OK
|  |  |  | 58.0 E | OK | 32.1 | OK
|  |  |  | 56.9 | OK | 37 | OK
|  |  |  | 52 | OK | 41.5 | OK
|  |  |  | 48.2 | OK | 45.4 | OK
|  |  |  | 43.5 | NO | 50.1 | OK
|  |  |  | 38.9 | OK | 55.5 | OK
|  |  |  | 34 | OK | 58.4 | OK
|  |  |  | 29.4 | OK
|  |  |  | 27.2 | OK
Note on B4: Ruffino, John: SIGN MISSING
Note on D4: Ruffino, John: NEEDS TO BE MOVED TO 34.8
Note on L4: Ruffino, John: NEEDS THE BEGIN SIGN
Note on J5: Ruffino, John: NEEDS DOT DECAL
Note on D6: Ruffino, John: SIGN MISSING
Note on B7: Ruffino, John: NEEDS DOT DECAL
Note on D7: Ruffino, John: DAMAGED NEEDS REPLACING
Note on D8: Ruffino, John: NEEDS DOT DECAL
Note on B9: Ruffino, John: DAMAGED NEEDS REPLACING
Note on H9: Ruffino, John: NEEDS THE BEGIN SIGN
Note on J9: Ruffino, John: SIGN MISSING
Note on B10: Ruffino, John: DAMAGED NEEDS REPLACING
Note on B11: Ruffino, John: SIGN INCORRECT OLD VERSION
Note on F11: Ruffino, John: NEEDS END SIGN
Note on B12: Ruffino, John: NEEDS DOT DECAL
Note on J13: Ruffino, John: NEEDS DOT DECAL
Note on J14: Ruffino, John: NEEDS DOT DECAL
Note on L14: Ruffino, John: SIGN MISSING
Note on F15: Ruffino, John: NEEDS THE BEGIN SIGN
Note on H15: Ruffino, John: NEEDS THE BEGIN SIGN
Note on J15: Ruffino, John: NEEDS END SIGN
Note on F16: Ruffino, John: NEEDS THE BEGIN SIGN
Note on F20: Ruffino, John: DAMAGED NEEDS REPLACING
Note on H22: Ruffino, John: NEEDS END SIGN
Note on F23: Ruffino, John: NEEDS DOT DECAL
Note on F24: Ruffino, John: NEEDS END SIGN

## SSP South
21DPP00572 - T3049 - NJDOT Sponsorship Programs Attachment 5 – Current SSP Sign Locations
State Farm Sign (57) Locations 05/24/19
RT. 295 - 25 |  |  |  | RT. 42 - 5 |  |  |  | RT. 55 - 10
NB |  | SB |  | NB |  | SB |  | NB |  | SB
16.1 | OK | 16.1 | OK | 7 | OK | 6.6 | OK | 20.3 | OK | 20.3 | OK
19.8 | OK | 21 | OK | 12.2 | OK | 9.2 | OK | 30.5 | OK | 30.5 | OK
24.9 | OK | 28.2 | OK |  |  | 13.5 | OK | 40.1 | OK | 39.1 | OK
28.9 | OK | 34.4 | OK |  |  |  |  | 51.1 | OK | 50.6 | OK
32.8 | OK | 38.6 | OK | RT. 76 - 2 |  |  |  | 56.9 | OK | 56 | OK
37.3 | OK | 42.3 | OK | WB |  | EB
43.9 | OK | 46.8 | OK | 1.4 | OK | 1.5 | OK | RT. 195 - 8
48.3 | OK | 51.6 | OK |  |  |  |  | WB |  | EB
52.9 | OK | 55.5 | OK | RT. 676 - 2 |  |  |  | 2.9 | OK | 1.3 | OK
57.8 | OK | 59.1 | OK | NB |  | SB |  | 7.2 | OK | 6.6 | OK
62.3 | OK | 63.4 | OK | 3.6 | OK | 2.8 | OK | 11.4 | OK | 11.3 | OK
69.1 | OK | 68.6 | OK |  |  |  |  | 16.3 | OK | 16.2 | OK
|  | 71.9 | OK
RT. 29 - 3
[8 empty] | NB |  | SB
[8 empty] | 0.8 | OK | 2.9 | OK
RT. 95 - 2 | [7 empty] | 2.8 | OK
NB |  | SB
0.8 | X | 0.9 | OK
Constitutes missing signage
Signs are in place 1 week before Memorial Day thru 1 week after Labor Day