## Sheet1
2017 MASTER SCHEDULE - NEW JERSEY DIVISION OF FISH AND WILDLIFE ELECTRONIC LICENSE SYSTEM
Attachment G
| Testing Begin | Testing Complete | Released to Prod | Test Lottery Run Date | PROD Lottery Date | Start Sale Date | End Sale Date | Notes for TESTING
Spring Turkey Applications |  | 2017-01-13 | 2017-01-20 | 2017-01-23 |  | 2017-01-25 | 2017-02-22 | Testing and Data Tables to be done ASAP
| 2016-12-15 |  |  |  | 02/27/2017 pm
Light Goose Harvest Report | With NLY | With NLY | With NLY | N/A |  | 2017-03-01 | 2017-04-30 23:59 | Internet Sales Site ONLY
Spring Turkey Awarded Permits | 2017-01-24 | 2017-02-17 | 2017-03-01 | N/A |  | 2017-03-06 | 3/27/2017 11:59PM EST
Spring Turkey OTC & Farmer Permits | 2017-03-01 | 2017-03-17 | 2017-03-30 | N/A |  | 4/03/2017 10AM EST | 05/26/2017 11:59PM EST | 319 - Farmer Permits available for pickup from 4/3/2017 - 5/26/2017
Comm-Marine Mid Year | 2017-05-01 | 2017-05-19 | 2017-06-01 | N/A |  | 2017-06-15 | 2018-06-30 | WebPOS ONLY for DFW Comm Marine LIDs ONLY
Mid Year License Release | 2017-05-01 | 2017-05-19 | 2017-06-01 | N/A |  | 06/15/2017 rifle | 2018-06-30 | Priv Names will have to be changed. Currently, the priv names for the rifle permit and waterfowl stamp have the year as part of the name.
07/01/2017 waterfowl, hip
Commercial Marine Licenses | 2017-08-01 | 2017-09-30 | 2017-10-31 | N/A |  | 2017-11-06 | 2018-12-31
ALL Deer, Fall Turkey Permits (including Farm) and BEAR | 2017-07-10 | 2017-08-25 | 2017-08-30 | N/A |  | MONDAY | Varies | Bear Permits will have a blackout period in the middle of their sales dates.
2017-09-11 10:00
10:00
Beaver/Otter Applications | 2017-08-15 | 2017-09-15 | 2017-09-26 | 2017-09-19 | 2017-11-02 | 2017-10-01 | 2017-10-31 | Beaver/Otter Apps tested simultaneously
Beaver/Otter Awarded Permits | 2017-09-21 | 2017-10-20 | 2017-11-03 | N/A |  | 2017-11-06 | 11/27/2017 at 11:59 pm
New License Year Rollout / PDF Changes | 2016-10-24 | 2016-11-18 | 2016-11-23 | N/A |  | 2016-12-01 | 2017-12-31
Beaver/Otter OTC Sales | 2017-11-06 | 2017-11-17 | 2016-11-30 | N/A |  | 2017-12-04 | 2018-02-10 | State will provide leftover numbers asap the morning of 12/01
Note on B4: Jenni Ryan: First full week of Jan (around Jan 7th) would be fine in future years