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To: 	All Interested Vendors {Bidders} 
Re:  	Bid Solicitation {RFP} # 17DPP00036
       	T2859 – NJDEP MSLA 1D Landfill Site, Landfill Closure Construction

       	Quote {Proposal} Submission Due Date: November 10, 2016 (2:00 p.m. ET)
	REVISED Quote {Proposal} Submission Due Date: November 29, 2016 (2:00 p.m. ET)


Bid Amendment {Addendum} #6

The following constitutes Bid Amendment {Addendum} #6 to the above referenced Bid Solicitation {RFP}:
  
Attached to this Bid Amendment {Addendum} are the answers to questions and additional bid information, which were inadvertently not included with Bid Amendment {Addendum} #5.

Please note that for all additions, deletions, clarifications and modifications to the Bid Solicitation {RFP} # 17DPP00036, please refer to the following revised documents:
	
	Revised Price Schedule T2859 10-25-16
	Revised RFP T2869 MSLA 1D Landfill Closure Project 10-25-16	
	Revised Attachment #2 T2859 MSLA 1D Technical Specifications 10-25-16
	Revised Drawings T2859 10-25-16 (Includes Drawings 5, 56, and 58)
	
	MSLA Site Improvements Project As-Built 2009 has been added as a reference document.

It is the sole responsibility of the Vendor {Bidder} to be knowledgeable of all of the additions, deletions, clarifications, and modifications to the Bid Solicitation {RFP} and/or the New Jersey Standard Terms and Conditions relative to this Bid Solicitation {RFP} as set forth in all Bid Amendments {Addenda}. 

All other instructions, terms, and conditions of the Bid Solicitation {RFP} shall remain the same.





Bid Solicitation [RFP} #17DPP00036
T2859 NJDEP MSLA 1D Landfill Site - Landfill Closure Construction  
 

Note: Some of the questions have been paraphrased in the interest of readability and clarity.  Each question is referenced by the appropriate Bid Solicitation {RFP} page number(s) and section where applicable.  

	#
	Page #
	RFP Section Reference
	Question (Bolded) and Answer

	1
	
	Sales Tax
	Section 5.5.12 - Please confirm the bidders are to include NJ Sales Tax on materials and that the project is not tax exempt.

Confirmed. Section 6.2 of the State of New Jersey Standard Terms and Conditions has been deleted. Please see Section 5.5.12 of the Bid Solicitation {RFP}.

	2
	
	Traffic Control
	Is a flagman required at the site entrance during the delivery of the imported soil trucks? (3.2.6.1)

It is up to the Vendor {Contactor}, as detailed in the Traffic Control Plan discussed in Technical Specification Section 3.2.6, whether a flagman will be needed for safety during deliveries, where the roadways are not blocked by the Vendor’s {Contractor’s} trucks.  Blocking or obstructing traffic on Harrison Ave or the Route I-280 ramp will require coordination with the Town and/or NJDOT who are expected to require flagmen and police support.  Note that left turns out of the site onto Harrison Ave are not allowed.


	3
	
	Wastefill
	Section 2.5.2 requires a 30-ton landfill compactor. Can the contractor determine what roller they want to use during the test strip to be performed?

Yes, on condition that the roller will have a minimum contact pressure of 80 pounds per square inch (psi).


	4
	
	Imported Fill
	2.8.2 Modified Fill I-13. This section states "Material from crushing operations will not be allowed. Screened material will be acceptable". Can stone crushings, stone dust or stone screenings be used?

Stone crushings, stone dust or stone screenings may be used below the geomembrane but not above the geomembrane (as they will not properly support the native species/ wildflower vegetation).


	5
	
	Air Monitoring
	Section 3.2.3.1 - Dust and Vapor Migration Plan refers to measuring dust at the property boundary. Appendix 1-HASP, section 2.6-Air Surveillance, 2.6.A,B.5,C.3,C.4,C.5 refers to daily air monitoring and data logs. Is the contractor required to do only handheld work zone area air monitoring or are stationary air monitoring stations at the property boundary perimeter also required? If so, how many?

The Vendor {Contractor} shall establish and implement a site-specific air-monitoring program to meet the requirements of this Blanket P.O. {Contract}.  The Dust and Vapor Migration Plan and Air Surveillance monitoring / sampling program shall be based on the Vendor’s {Contractor’s} Means and Methods in completing its work and shall be sufficient to document that the property boundary dust standard is met.  The site is approximately 90 acres and the Vendor {Contractor} may have multiple crews working separate areas simultaneously.  As such, the Vendor {Contractor} may utilize a location specific approach to assure safety and compliance in each work zone. For stationary locations, the Vendor {Contractor} shall safeguard against incorrectly captured or missed data.


	6
	
	Seeding
	Section 2.24.3-1, can the oats and permanent native seed mix be installed at the same time?

Install as specified.  The oats and permanent native seed mix can be installed one after the other; however, they cannot be put in the same mix for application. The oats serve as a cover crop for the native seed mix.


	7
	
	Micropiles
	Section 2.28.10 - are pile loads tests / test piles required by the Engineer?

Yes, for driven piles for each type/size/capacity of pile, pile performance shall be verified by three (Pile Dynamic Analysis) (PDA) Tests (minimum) in accordance with ASTM D4945  (Standard Test Method for High-Strain Dynamic Testing of Deep Foundations). For drilled shafts with a maximum allowable capacity of 40 tons and micropiles with a maximum allowable capacity of 20 tons, no pile load tests are required.


	8
	
	Operations and Maintenance
	Are there any minimum qualifications for the O&M personnel for the gas flare/blower system O&M?

O&M personnel shall be capable of performing the O&M tasks described in the Specifications and as required by the manufacturer(s).  Vendor {Contractor} is responsible for determining if their personnel/contractors are capable of performing the tasks.  Tasks not performed accurately/ satisfactorily shall be corrected and may lead to penalties if work is not corrected.  Additionally, all personnel shall have OSHA health and safety training appropriate for their role on the project.


	9
	
	Gas Flare
	What warranty is required on the flare?


See Section 5.5.9 and Section 11-Subsection 5.11 of the Bid Solicitation {RFP}.

	10
	
	Operations and Maintenance
	4.2-7 - Task 2 - Roadway Repair: do we only assume using recycled concrete aggregate type B, not asphalt?

Yes.


	11
	
	Operations and Maintenance
	4.2-7 - Task 7 - Contractor is not required to mow the entire landfill?

Mowing is only required in the areas in areas described in Technical Specification Section 4.2.1.4, Task 7, and not the entire landfill.


	12
	
	Operations and Maintenance
	4.2-8 - Task 7 - Vegetation Control: please confirm that the contractor is required to apply herbicide on foot by DEP licensed commercial applicator 6 to 8 times per year, for 2 years for all 80 acres?

Yes.


	13
	
	Operations and Maintenance
	4.2-15 - Natural Gas Connection: is a licensed electrician necessary to inspect the propane system every month for 2 years?

Inspector shall have appropriate certifications and qualifications to perform inspections.  Vendor {Contractor} is responsible for ensuring inspections are done properly and in compliance with propane systems.


	14
	
	Operations and Maintenance
	4.2-9 / 16: Emergency Response: the number of alarm conditions for the pump stations, gas flare/blowers or generators cannot be anticipated. Specifically for the flare regarding alarms or flare shut-offs. Can the Engineer propose a certain number of emergency response events for the contractors to include?

No. It is the Vendor’s {Contractor’s} responsibility to properly tune and/or maintain the pump stations, generators, and gas extraction system and flare to minimize alarms and shutdowns.


	15
	
	Operations and Maintenance
	4.2.1 & 2 - The contractor is responsible for leachate testing quarterly in these 2 items for the 2 year O&M. The PVSC attachment does not provide the testing parameters. Can you provide the testing parameters for PVSC and KMUA quarterly testing?

PVSC will not provide testing parameters until the facility is ready for operation.  For bidding purposes Vendor {Contractor} shall assume testing includes: Metals, BOD, TSS, VOCs, SVOCs, TTO, TTVO, PCB, Pesticides, cyanide, and Petroleum Hydrocarbons.  Additional parameters (if required) will be addressed by change order.  


	16
	
	Operations and Maintenance
	4.2-13 - the hydrostatic pressure of the cut-off wall will be monitored on a monthly basis. Does this mean taking water level measurements at the 12 new monitoring wells?

Yes.


	17
	
	Operations and Maintenance
	4.2-9 - Task 10-Leachate Collection - is it the Engineer's intent that the 8600 lf of 8-inch perforated leachate collection pipe be high-pressure water-jet cleaned every year?

The 8-inch leachate collection pipe shall not be high-pressure water-jet cleaned.  All of the forcemain pipe shall be high-pressure water-jet cleaned once. The Engineer will direct when that cleaning will occur.


	18
	
	Electricity
	Is the North Pump Station electricity paid directly by the KMUA?

Yes.


	19
	
	Wastefill Excavation Making Grade
	Section 2.4.1 General- Wastefill and Earth Excavation: states that final grades of the final cap shall be as per the revised drawings provided by the engineer. The drawings will incorporate the existing grades that are to be established by the pre-construction survey. If after the subgrade and final grade are establish in an area but settles do to the nature of the garbage decaying or compacting from the weight of the cover material is the contract required to add cover material to bring back the area to grade.

Depending on the amount of settlement, the Engineer may require additional imported fill or regrading to attain subgrade elevations.  This will be handled at the time using “if and where directed” items or a Blanket P.O. [Contract} modification.


	20
	
	Wastefill Excavation Making Grade
	Addendum 4 added requirements to section 2.4 .1 requiring that subgrade areas that are excavated to grade are to be compacted and if settlement takes place additional material has to be add to make grade at the contractors cost, once grade is established what is the duration of time for the settlement? Does this hold for fill areas where wastefill is placed?

The following statement above “if settlement takes place additional material has to be add to make grade at the contractors cost” is not correct.  The added statement provided in Addendum #4 is as follows.  “The Areas in which excavation is performed to achieve subgrade elevations will require Contractor compaction before placement of cap components. Compaction shall be performed as outlined in Section 2.5, Wastefill Placement and Compaction. If after compaction any excavation area is below subgrade elevation, Contractor shall add Wastefill material, compact, and re-survey until subgrade elevation is achieved at no additional cost to the State.”

Depending on the amount of settlement which takes place after compacted subgrade is established, Engineer may require additional wastefill or imported fill be provided to re-set grades.  This would be handled at the time using “if and where directed” items or a Blanket P.O. {Contract} modification.


	21
	
	Sect. 3.2.5 Security
	Will full time security personnel be required at the site during the 2 yr. post-construction Operational Maintenance period as well?

No.

	22
	
	Daily Cover
	Since there is over 140,000 cy of wastefill excavation generated from items, 36,38 & 39, estimating the amount of daily cover required will be extremely difficult to predict. Please consider creating an item for daily cover rather than make it the contractor's responsibility, in order to make it more fair to both the contractor and the state.

In accordance with N.J.A.C. 7:26-2A.8, daily cover as per N.J.A.C. 7:27-2A.8, may be required during landfill grading operations.  Daily cover material shall be installed only if and where directed by the Engineer.  The determination as to daily cover material requirements and suitability for use in any given area will be made solely by the Engineer.  Cover material will be paid under Items 2.4.1, 2.4.3, and 2.8.2.  The Engineer shall have the right to direct the location for placement of excavated materials such that, to the extent possible, suitable materials, are used as daily cover.


	23
	
	Flare O&M Response
	Given that the frequency of flare system alarms due to things beyond the Contractor?s control is unknown, can the response to flare system alarms to be compensated as an additional cost?

No, it is the Vendor’s {Contractor’s} responsibility to properly tune the gas extraction system and flare to minimize alarms and shutdowns


	24
	
	Flare - 2.19
	Is flare stack testing required? If so, what parameters?

Yes.  The CD given out at the Mandatory Vendor’s {Bidder’s’} Site Visit contains the Air Permit for the Gas Flare and testing requirements.  Please refer to the Permit.


	25
	
	Slurry Wall
	Section 2.6.8.8 refers to taking cube samples for permeability. CB walls usually use grout cylinders.

Grout cylinders in lieu of cube samples are acceptable.


	26
	
	Slurry Wall
	Section 2.6.8.8 refers to taking cube samples for permeability. CB walls usually use grout cylinders.

Grout cylinders in lieu of cube samples are acceptable.


	27
	
	
	We ask for clarification of the geocomposite.  Section 2.13.2 asks for a peel of 2lb/in min and 4lb/in avg whereas Table 2.13-1 specifies 1 lb which is consistent with GRI GC-8.  Pls clarify a 1lb/in value is required.

A peel strength of 1lb/inch is acceptable.


	28
	
	
	We ask that black geotextile be acceptable for the geocomposite.  White fabrics are no longer used for composites and are not as UV resistant as black geotextiles.  White also increases the chance of snow blindness which is a safety hazard.

Black geotextile on the geocomposite is acceptable.


	29
	
	
	No current geocomposite manafacturer with a 275 mil thick geocomposite can meet your transmissivity values specified.  I have attached to two leading manufacturers spec specs for you review and approval.  Otherwise, could you supply us with a manufacturer that can meet your spec?

The minimum geonet thickness is 200 mil, a thicker geonet may be required to meet transmissivity requirements.


	30
	
	NJ Sales Tax
	RFP section 1.1 (page 9) says the Contractor shall pay State sales tax. RFP section 11.0, subsection 6.2 (page 100) says the bid price must not include State sales tax, etc. Please clarify if the Contractor will have to pay State sales tax on permanent materials.

See response to Question #1.


	31
	
	Tax Exempt Status
	Please clarify if the project is tax exempt.

See response to Question #1.


	32
	
	Contract - Taxes
	Section 5.5.12 - Please confirm the bidders are to include NJ Sales Tax on materials and that the project is not tax exempt. 

See response to Question #1.


	33
	
	Not Tax Exempt?
	RFP section 1.1 (purpose and intent) indicates the contractor is to pay for several taxes that are typically exempt on public projects. Please confirm this is correct as written that the project is NOT exempt tax exempt.

Confirmed. See response to Question #1.
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