## Task 1
A: Deliverable 1: Ongoing
Phase # | Phase | Release | Proposed Deliverable # | Proposed Deliverables | Deliverable Frequency | Bidder Agrees to Produce and Meet? (Yes/No)
1.1 | Ongoing | Ongoing | 1.1.1 | Monthly Status Reports (MSRs) | End of the Month
|  |  | 1.1.2 | Weekly Status Reports (WSRs) | End of the Week
|  |  | 1.1.3 | Project Management Plan (PMP) | Submit at pre-planning stage and update until formal CARB Project Manager (PM) acceptance is received
|  |  | 1.1.4 | Task Accomplishment Plan (TAP) | End of the Month
|  |  | 1.1.5 | Project Schedule Development and Updates | First Draft at Planning Stage and Updates are completed every Week
|  |  | 1.1.6 | Meeting Participation, Setup and Documentation | Ongoing
|  |  | 1.1.7 | Meeting Notes Development | Ongoing
|  |  | 1.1.8 | Deliverable Tracker Steps Execution | Ongoing
|  |  | 1.1.9 | Deliverable Tracker Updates/Communication | Ongoing
|  |  | 1.1.10 | Deliverables' documentation Update and Resubmission | Ongoing
|  |  | 1.1.11 | Deliverables Routing Process for Signatures | Ongoing
|  |  | 1.1.12 | Action Items Log, Issues and Risks Register, Decision Log Documentation | Ongoing

## Task 2
B: Deliverable 2: BECRT Minimum Viable Product (MVP)
Phase # | Phase | Release | Proposed Deliverable # | Proposed Deliverables | Completion Timeframe | Bidder Agrees to Produce and Meet? (Yes/No)
2.1 | Planning | BECRT Minimum Viable Product (MVP) | 2.1.1 | Vendor Onboarding Sessions Participation (PMO Review) | Beginning of Planning
|  |  | 2.1.2 | Vendor Onboarding Sessions and Assignments completion (PMO Review) | Beginning of Planning
|  |  | 2.1.3 | Implementation Plan | During Planning
|  |  | 2.1.4 | SharePoint Site Setup and Usage (PMO Review) | During Planning
|  |  | 2.1.5 | Project documentation Setup and Sharing (PMO Review) | During Planning
|  |  | 2.1.6 | Product Roadmap | During Planning
|  |  | 2.1.7 | Training Plan | During Planning
|  |  | 2.1.8 | Business Continuity Plan | During Planning
|  |  | 2.1.9 | Testing Plan | During Planning
|  |  | 2.1.10 | Azure DevOps Product Backlog Hierarchy Setup and Updates | End of Planning
|  |  | 2.1.11 | Azure DevOps Product Backlog, Sprint Backlog, Testing Artifacts and Reporting Metrics Setup and Updates | End of Planning
|  |  | 2.1.12 | Go-Live Plan | End of Planning
|  |  | 2.1.13 | Release Plan | End of Planning
2.2 | Analysis | BECRT Minimum Viable Product (MVP) | 2.2.1 | User Story Development, Updates and Finalization | During Analysis
|  |  | 2.2.2 | Azure DevOps Sprint Allocation exports | End of Analysis
2.3 | Design | BECRT Minimum Viable Product (MVP) | 2.3.1 | Architecture Board Presentation Materials | Initiation of Design
|  |  | 2.3.2 | Architecture Board Approval | Initiation of Design
|  |  | 2.3.3 | California Cloud Services Assessment (CCSA) Participation | During Design
|  |  | 2.3.4 | California Cloud Services Assessment (CCSA) Documentation | During Design
|  |  | 2.3.5 | Entity Relationship Diagram (ERD) | During Design
|  |  | 2.3.6 | Data Dictionary | During Design
|  |  | 2.3.7 | Enterprise Data Questionnaire | During Design
|  |  | 2.3.8 | Business Glossary | During Design
|  |  | 2.3.9 | Enterprise Data Review | During Design
|  |  | 2.3.10 | Database Review | During Design
|  |  | 2.3.11 | Privacy Impact Assessment (PIA) | During Design
|  |  | 2.3.12 | eDiscovery and Litigation Hold Policy | During Design
|  |  | 2.3.13 | Privacy Notice | During Design
|  |  | 2.3.14 | FIPS Data Classification Document | During Design
|  |  | 2.3.15 | STRIDE Model | During Design
|  |  | 2.3.16 | Information Technology Risk Assessment Sessions | During Design
|  |  | 2.3.17 | Information Technology Risk Assessment Document | During Design
|  |  | 2.3.18 | Firewall Design Diagram | During Design
|  |  | 2.3.19 | System Security Plan | During Design
|  |  | 2.3.20 | Business Impact Analysis (BIA) | End of Design
|  |  | 2.3.21 | Technology Recovery Plan (TRP) | End of Design
|  |  | 2.3.22 | Information Security Incident Response Plan (ISIRP) | End of Design
|  |  | 2.3.23 | Visual Design Approval | End of Design
2.4 | Execution | BECRT Minimum Viable Product (MVP) | 2.4.1 | Database Request Form Document | Initiation of Execution
|  |  | 2.4.2 | Registration, Fee Module Banner, Data Submission, Reference Tables, Data Query, Filter and Export Results Modules Execution | End of Execution
|  |  | 2.4.3 | Requirements Traceability Matrix (RTM) | End of Execution
|  |  | 2.4.4 | Database Updates | During Execution
|  |  | 2.4.5 | Test Cases | End of Execution
2.5 | Testing | BECRT Minimum Viable Product (MVP) | 2.5.1 | Test Execution | During Testing
|  |  | 2.5.2 | Vulnerability Scan Reports | During Testing
|  |  | 2.5.3 | Security Review | During Testing
|  |  | 2.5.4 | User Interface Review | During Testing
|  |  | 2.5.5 | Code Review | During Testing
|  |  | 2.5.6 | DevOps Review | During Testing
|  |  | 2.5.7 | GIS Review | During Testing
|  |  | 2.5.8 | Infrastructure Review | During Testing
|  |  | 2.5.9 | Defect Management Process Execution | During Testing
|  |  | 2.5.10 | Test Reports | During Testing
2.6 | Deployment | BECRT Minimum Viable Product (MVP) | 2.6.1 | Release Activities Development | Initiation of Deployment
|  |  | 2.6.2 | User Manuals (Documentation Review) | During Deployment
|  |  | 2.6.3 | Training Materials | During Deployment
|  |  | 2.6.4 | Standard Operating Procedures (SOP) | During Deployment
|  |  | 2.6.5 | Information Technology Risk Assessment Updates | During Deployment
|  |  | 2.6.6 | System Security Plan Updates | During Deployment
|  |  | 2.6.7 | Knowledge Transfer Materials | During Deployment
|  |  | 2.6.8 | Knowledge Transfer Sessions | During Deployment
|  |  | 2.6.9 | Lessons Learned Documentation | End of Deployment
|  |  | 2.6.10 | Lessons Learned Sessions | End of Deployment
|  |  | 2.6.11 | Release Activities Completion | End of Deployment
|  |  | 2.6.12 | Release Log | End of Deployment

## Task 3
C. Deliverable 3: BECRT Post Minimum Viable Product – Release 1
Phase # | Phase | Release | Proposed Deliverable # | Proposed Deliverables | Completion Date | Bidder Agrees to Produce and Meet? (Yes/No)
3.1 | Planning | BECRT Post Minimum Viable Product – Release 1 | 3.1.1 | Project documentation Setup and Sharing (PMO Review) | During Planning
|  |  | 3.1.2 | Azure DevOps Product Backlog Hierarchy Setup and Updates | End of Planning
|  |  | 3.1.3 | Azure DevOps Product Backlog, Sprint Backlog, Testing Artifacts and Reporting Metrics Setup and Updates | End of Planning
|  |  | 3.1.4 | Release Plan | End of Planning
3.2 | Analysis | BECRT Post Minimum Viable Product – Release 1 | 3.2.1 | User Story Development, Updates and Finalization | During Analysis
|  |  | 3.2.2 | Azure DevOps Sprint Allocation exports | End of Analysis
3.3 | Design | BECRT Post Minimum Viable Product – Release 1 | 3.3.1 | Entity Relationship Diagram (ERD) | During Design
|  |  | 3.3.2 | Data Dictionary | During Design
|  |  | 3.3.3 | Enterprise Data Questionnaire | During Design
|  |  | 3.3.4 | Business Glossary | During Design
|  |  | 3.3.5 | Enterprise Data Review | During Design
|  |  | 3.3.6 | Database Review | During Design
|  |  | 3.3.7 | Visual Design Approval | End of Design
3.4 | Execution | BECRT Post Minimum Viable Product – Release 1 | 3.4.1 | Registration, Ledger, Data Query, Filter and Export Results Modules Execution | Initiation of Execution
|  |  | 3.4.2 | Requirements Traceability Matrix (RTM) | End of Execution
|  |  | 3.4.3 | Database Updates | During Execution
|  |  | 3.4.4 | Test Cases | End of Execution
3.5 | Testing | BECRT Post Minimum Viable Product – Release 1 | 3.5.1 | Test Execution | During Testing
|  |  | 3.5.2 | Vulnerability Scan Reports | During Testing
|  |  | 3.5.3 | Security Review | During Testing
|  |  | 3.5.4 | User Interface Review | During Testing
|  |  | 3.5.5 | Code Review | During Testing
|  |  | 3.5.6 | DevOps Review | During Testing
|  |  | 3.5.7 | GIS Review | During Testing
|  |  | 3.5.8 | Infrastructure Review | During Testing
|  |  | 3.5.9 | Defect Management Process Execution | During Testing
|  |  | 3.5.10 | Test Reports | During Testing
3.6 | Deployment | BECRT Post Minimum Viable Product – Release 1 | 3.6.1 | Release Activities Development | Initiation of Deployment
|  |  | 3.6.2 | User Manuals (Documentation Review) | During Deployment
|  |  | 3.6.3 | Training Materials | During Deployment
|  |  | 3.6.4 | Standard Operating Procedures (SOP) | During Deployment
|  |  | 3.6.5 | Information Technology Risk Assessment Updates | During Deployment
|  |  | 3.6.6 | System Security Plan Updates | During Deployment
|  |  | 3.6.7 | Knowledge Transfer Materials | During Deployment
|  |  | 3.6.8 | Knowledge Transfer Sessions | During Deployment
|  |  | 3.6.9 | Lessons Learned Documentation | End of Deployment
|  |  | 3.6.10 | Lessons Learned Sessions | End of Deployment
|  |  | 3.6.11 | Release Activities Completion | End of Deployment
|  |  | 3.6.12 | Release Log | End of Deployment

## Task 4
D. Deliverable 4: BECRT Post Minimum Viable Product – Release 2
Phase # | Phase | Release | Proposed Deliverable # | Proposed Deliverables | Completion Date | Bidder Agrees to Produce and Meet? (Yes/No)
4.1 | Planning | BECRT Post Minimum Viable Product – Release 2 | 4.1.1 | Project documentation Setup and Sharing (PMO Review) | During Planning
|  |  | 4.1.2 | Azure DevOps Product Backlog Hierarchy Setup and Updates | End of Planning
|  |  | 4.1.3 | Azure DevOps Product Backlog, Sprint Backlog, Testing Artifacts and Reporting Metrics Setup and Updates | End of Planning
|  |  | 4.1.4 | Release Plan | End of Planning
4.2 | Analysis | BECRT Post Minimum Viable Product – Release 2 | 4.2.1 | User Story Development, Updates and Finalization | During Analysis
|  |  | 4.2.2 | Azure DevOps Sprint Allocation exports | End of Analysis
4.3 | Design | BECRT Post Minimum Viable Product – Release 2 | 4.3.1 | Entity Relationship Diagram (ERD) | During Design
|  |  | 4.3.2 | Data Dictionary | During Design
|  |  | 4.3.3 | Enterprise Data Questionnaire | During Design
|  |  | 4.3.4 | Business Glossary | During Design
|  |  | 4.3.5 | Enterprise Data Review | During Design
|  |  | 4.3.6 | Database Review | During Design
|  |  | 4.3.7 | Visual Design Approval | End of Design
4.4 | Execution | BECRT Post Minimum Viable Product – Release 2 | 4.4.1 | Data Submission, Fee Calculation and Collection, Data Query, Filter and Export Results Modules Execution | End of Execution
|  |  | 4.4.2 | Requirements Traceability Matrix (RTM) | End of Execution
|  |  | 4.4.3 | Database Updates | During Execution
|  |  | 4.4.4 | Test Cases | End of Execution
4.5 | Testing | BECRT Post Minimum Viable Product – Release 2 | 4.5.1 | Test Execution | During Testing
|  |  | 4.5.2 | Vulnerability Scan Reports | During Testing
|  |  | 4.5.3 | Security Review | During Testing
|  |  | 4.5.4 | User Interface Review | During Testing
|  |  | 4.5.5 | Code Review | During Testing
|  |  | 4.5.6 | DevOps Review | During Testing
|  |  | 4.5.7 | GIS Review | During Testing
|  |  | 4.5.8 | Infrastructure Review | During Testing
|  |  | 4.5.9 | Defect Management Process Execution | During Testing
|  |  | 4.5.10 | Test Reports | During Testing
4.6 | Deployment | BECRT Post Minimum Viable Product – Release 2 | 4.6.1 | Release Activities Development | Initiation of Deployment
|  |  | 4.6.2 | User Manuals (Documentation Review) | During Deployment
|  |  | 4.6.3 | Training Materials | During Deployment
|  |  | 4.6.4 | Standard Operating Procedures (SOP) | During Deployment
|  |  | 4.6.5 | Information Technology Risk Assessment Updates | During Deployment
|  |  | 4.6.6 | System Security Plan Updates | During Deployment
|  |  | 4.6.7 | Knowledge Transfer Materials | During Deployment
|  |  | 4.6.8 | Knowledge Transfer Sessions | During Deployment
|  |  | 4.6.9 | Lessons Learned Documentation | End of Deployment
|  |  | 4.6.10 | Lessons Learned Sessions | End of Deployment
|  |  | 4.6.11 | Release Activities Completion | End of Deployment
|  |  | 4.6.12 | Release Log | End of Deployment

## Task 5
E. Deliverable 5: BECRT Post Minimum Viable Product – Release 3
Phase # | Phase | Release | Proposed Deliverable # | Proposed Deliverables | Completion Date | Bidder Agrees to Produce and Meet? (Yes/No)
5.1 | Planning | BECRT Post Minimum Viable Product – Release 3 | 5.1.1 | Project documentation Setup and Sharing (PMO Review) | During Planning
|  |  | 5.1.2 | Azure DevOps Product Backlog Hierarchy Setup and Updates | End of Planning
|  |  | 5.1.3 | Azure DevOps Product Backlog, Sprint Backlog, Testing Artifacts and Reporting Metrics Setup and Updates | End of Planning
|  |  | 5.1.4 | Release Plan | End of Planning
5.2 | Analysis | BECRT Post Minimum Viable Product – Release 3 | 5.2.1 | User Story Development, Updates and Finalization | During Analysis
|  |  | 5.2.2 | Azure DevOps Sprint Allocation exports | End of Analysis
5.3 | Design | BECRT Post Minimum Viable Product – Release 3 | 5.3.1 | Entity Relationship Diagram (ERD) | During Design
|  |  | 5.3.2 | Data Dictionary | During Design
|  |  | 5.3.3 | Enterprise Data Questionnaire | During Design
|  |  | 5.3.4 | Business Glossary | During Design
|  |  | 5.3.5 | Enterprise Data Review | During Design
|  |  | 5.3.6 | Database Review | During Design
|  |  | 5.3.7 | Visual Design Approval | End of Design
5.4 | Execution | BECRT Post Minimum Viable Product – Release 3 | 5.4.1 | Reports, Correspondence Functionality, Filter and Export Results Modules Execution | End of Execution
|  |  | 5.4.2 | Requirements Traceability Matrix (RTM) | End of Execution
|  |  | 5.4.3 | Database Updates | During Execution
|  |  | 5.4.4 | Test Cases | End of Execution
5.5 | Testing | BECRT Post Minimum Viable Product – Release 3 | 5.5.1 | Test Execution | During Testing
|  |  | 5.5.2 | Vulnerability Scan Reports | During Testing
|  |  | 5.5.3 | Security Review | During Testing
|  |  | 5.5.4 | User Interface Review | During Testing
|  |  | 5.5.5 | Compliance Analysis | During Testing
|  |  | 5.5.6 | Code Review | During Testing
|  |  | 5.5.7 | DevOps Review | During Testing
|  |  | 5.5.8 | Reporting Review | During Testing
|  |  | 5.5.9 | GIS Review | During Testing
|  |  | 5.5.10 | Infrastructure Review | During Testing
|  |  | 5.5.11 | Defect Management Process Execution | During Testing
|  |  | 5.5.12 | Test Reports | During Testing
5.6 | Deployment | BECRT Post Minimum Viable Product – Release 3 | 5.6.1 | Release Activities Development | Initiation of Deployment
|  |  | 5.6.2 | User Manuals (Documentation Review) | During Deployment
|  |  | 5.6.3 | Training Materials | During Deployment
|  |  | 5.6.4 | Standard Operating Procedures (SOP) | During Deployment
|  |  | 5.6.5 | Information Technology Risk Assessment Updates | During Deployment
|  |  | 5.6.6 | System Security Plan Updates | During Deployment
|  |  | 5.6.7 | Knowledge Transfer Materials | During Deployment
|  |  | 5.6.8 | Knowledge Transfer Sessions | During Deployment
|  |  | 5.6.9 | Lessons Learned Documentation | End of Deployment
|  |  | 5.6.10 | Lessons Learned Sessions | End of Deployment
|  |  | 5.6.11 | Release Activities Completion | End of Deployment
|  |  | 5.6.12 | Release Log | End of Deployment
|  |  | 5.6.13 | Maintenance & Operations (M&O) Plan | End of Deployment
|  |  | 5.6.14 | Transition Plan | End of Deployment